## Organizational Chart
STEERING COMMITTEE
Country Manager | Galante
Corporate Sales Director | Marongiu
Corporate Service Director | Bellet
Corporate CIO | Ballerio
Corporate CFO | Albertario
Corporate Controller | Arena
Argentina Project Leader | Cornu
Europe Project Leader | Invernizzi
PROJECT MANAGEMENT TEAM
Argentina Project Leader | Cornu
Europe Project Leader | Invernizzi
Project Manager ICT | Pagliara
Project Manager Service AR | Pena
Finance Manger AR | Tersse
SAP Integration Responsible | Pena
LOCAL KEY USERS |  | EPTA KEY USERS |  | EPTA ICT TEAM
Service Manager | Sosa | Service Master Data | Guglielminetti | Service Procurement | ???
Service Master Data | Gordiola | Service Procurement - Industry | D'Incà | Service Spare Parts | ???
Service Procurement | Saenz | Service Procurement - Purchasing | Dalla Caneva | Service Maintenance | ???
Service Back Office | Pena | Wharehouse Management | D'Incà | Wharehouse Management | ???
Wharehouse Management & Logistics | Saenz | Spare Parts Logistics | Bassotti | Logistics | ???
Service Maintenance - Supervisor | Sosa | Service Maintenance - Contracting | Montanari | Finance | ???
Finance | Uranga | Service Maintenance - Supervisor (I) | ??? | Controlling | ???
Controlling | Altamir | Service Maintenance - Supervisor (E) | ??? | Service APP | ???
ICT AR | Pena | Invoicing | Falco | Development | ???
|  | Controlling | De Bona

## Project Plan
[5 empty] | SEPTEMBER |  |  |  |  | OCTOBER |  |  |  | NOVEMBER |  |  |  |  | DECEMBER JANUARY |  |  |  |  | FEBRUARY |  |  |  | MARCH
Phase | Subject | Task | Owner | Local Team | w35 | w36 | w37 | w38 | w39 | w40 | w41 | w42 | w43 | w44 | w45 | w46 | w47 | w48 | w49 | w50 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10
Project Preparation | Master Data Preparation | Equipments List and attributes | bar: SEPTEMBER w35 to OCTOBER w43
Spare Parts Codes (with attributes) | bar: SEPTEMBER w35 to OCTOBER w43
Spare Parts Pricing | bar: SEPTEMBER w35 to OCTOBER w43
Finished Products BOMs and SP Explosion | bar: SEPTEMBER w35 to OCTOBER w43
Customers List (with attributes) | bar: SEPTEMBER w35 to OCTOBER w43
Service Engineers List by Regional Teams | bar: SEPTEMBER w35 to OCTOBER w43
Master Data Management | Master Data Fulfillment | Equipments List by Customer Site (with attributes) | bar: NOVEMBER w44 to NOVEMBER w47
Spare Parts List (with attributes) | bar: NOVEMBER w44 to NOVEMBER w47
Spare Parts Pricing | bar: NOVEMBER w44 to NOVEMBER w47
Customers List (with attributes) | bar: NOVEMBER w44 to NOVEMBER w47
Service Engineers List by Regional Teams | bar: NOVEMBER w44 to NOVEMBER w47
FIT-GAP Analysis | Spareparts: Process Mapping and FIT-GAP Analysis | Compare existing processes and procedures with the Epta Argentina requirements | bar: SEPTEMBER w36 to SEPTEMBER w38
| Spareparts: Process GAP Implementation | Adjustments on new Service Procedures | bar: SEPTEMBER w38 to SEPTEMBER w39
| Spareparts: Process Validation | Check Point | bar: OCTOBER w40
FIT-GAP Analysis | Maintenance: Process Mapping and FIT-GAP Analysis | Compare existing processes and procedures with the Epta Argentina requirements (i.e. refurbishment) | bar: SEPTEMBER w36 to OCTOBER w40
| Maintenance: Process GAP Implementation | Adjustments on new Service Procedures | bar: OCTOBER w41 to OCTOBER w42
| Maintenance: Process Validation | Check Point | bar: OCTOBER w43
FIT-GAP Analysis | Warehouse Management - Inbound Flow: Process Mapping and FIT-GAP Analysis | Compare existing processes and procedures with the Epta Argentina requirements | bar: SEPTEMBER w36 to OCTOBER w43
| Warehouse Management - Inbound Flow: Process GAP Implementation | Adjustments on new Service Procedures | bar: OCTOBER w43 to NOVEMBER w44
| Warehouse Management - Inbound Flow: Process Validation | Check Point | bar: NOVEMBER w45
FIT-GAP Analysis | Warehouse Management - Outbound Flow: Process Mapping and FIT-GAP Analysis | Compare existing processes and procedures with the Epta Argentina requirements | bar: OCTOBER w40 to NOVEMBER w45
| Warehouse Management - Outbbound Flow: Process GAP Implementation | Adjustments on new Service Procedures | bar: NOVEMBER w46
| Warehouse Management - Outbound Flow: Process Validation | Check Point | bar: NOVEMBER w47
FIT-GAP Analysis | Reporting: Business Intelligence Model and FIT-GAP Analysis | Compare existing processes and procedures with the Epta Argentina requirements | bar: SEPTEMBER w36 to OCTOBER w40
| Reporting: Business Intelligence Model GAP Implementation | Adjustments on new Service Procedures | bar: OCTOBER w41
| Reporting: Business Intelligence Model Validation | Check Point | bar: OCTOBER w42
Proc. | Hardware Provisioning & Contracts | PC, Printers, Smart Phones or Tablets, Mobile Contract, Email | bar: SEPTEMBER w35 to NOVEMBER w45
Deliverables | Processes & Procedures Documentation | for Finance Department | bar: NOVEMBER w45 to NOVEMBER w46
for Buyers | bar: NOVEMBER w45 to NOVEMBER w46
for Service coordinators | bar: NOVEMBER w45 to NOVEMBER w46
for Call Centre | bar: NOVEMBER w45 to NOVEMBER w46
for Service Engineers | bar: NOVEMBER w45 to NOVEMBER w46
Acceptance | Process Test with Key Users | for Finance Department | bar: NOVEMBER w47 to DECEMBER JANUARY w50
for Buyers | bar: NOVEMBER w47 to DECEMBER JANUARY w50
for Service coordinators | bar: NOVEMBER w47 to DECEMBER JANUARY w50
for BackOffice and Internal Vendors | bar: NOVEMBER w47 to DECEMBER JANUARY w50
for Service Engineers | bar: NOVEMBER w47 to DECEMBER JANUARY w50
Training | Training to End-Users | for Service Master Data Team | bar: DECEMBER JANUARY w50
for Service Managers | bar: DECEMBER JANUARY w50
for Spare Parts Buyers | bar: DECEMBER JANUARY w50
for Service Back Office | bar: DECEMBER JANUARY w50
for Service Engineers (by Region) | bar: DECEMBER JANUARY w50
for Warehouse operators | bar: DECEMBER JANUARY w50
Deploy | Go-Live | System Preparation | bar: NOVEMBER w48 to DECEMBER JANUARY w50
| Post Go-Live (On site) | Process Control & Adjustments
| Post Go-Live (Remote) | Process Control & Adjustments